## Backlog
ID | Epic | Story | As a… | I want… | So that… | Sprint | Points | Status | Risk | ADR / Note
IB-12 | Security & Compliance | Rotate all legacy production-looking tokens | platform owner | every secret that ever sat in env.yaml revoked and reissued | the previously-leaked tokens can't be used against us | Sprint-2 | 2 | Ready | R-009 | —
IB-13 | Security & Compliance | Scrub leaked tokens from git history | platform owner | the leaked tokens permanently removed from every reachable commit | the repo can be cloned safely | Sprint-2 | 3 | Ready | R-009 | —
IB-14 | Security & Compliance | Install pre-commit secret scanner (gitleaks) | contributor | any attempt to commit a real secret to be blocked locally | R-009 never repeats itself | Sprint-2 | 2 | Ready | R-009 | —
IB-15 | Security & Compliance | Enable GitHub secret scanning + push protection | platform owner | GitHub to refuse pushes containing known secret patterns | the fence is enforced at SCM level too | Sprint-2 | 1 | Ready | R-009 | —
IB-16 | Security & Compliance | Move RabbitMQ from user/pass to TLS-cert auth | platform team | Messor and Curator to authenticate to RabbitMQ with mTLS | a leaked AMQPS URL alone isn't enough | Sprint-3 | 5 | Ready | R-009 | —
IB-17 | Security & Compliance | External penetration test before second user cohort | platform owner | an independent pentest report before scaling past 50 users | I have evidence-based assurance | Sprint-4 | 3 | Ready | R-009 | —
IB-18 | Reliability & Resilience | Production Dockerfile + health endpoints for both services | platform owner | every container to expose /healthz and /readyz | Docker/DO can replace unhealthy instances | Sprint-2 | 3 | Ready | R-005 | Was-INK-3
IB-19 | Reliability & Resilience | Tenacity retry wrapper around outbound HTTP | pipeline | every Anthropic/OpenAI/Spaces/outlet call to retry with backoff | one hiccup doesn't drop a whole cycle | Sprint-2 | 3 | Ready | R-002,R-003 | Was-INK-6
IB-20 | Reliability & Resilience | Per-outlet circuit breaker in Messor | harvester | to skip outlets that have failed 5 consecutive cycles | a blocked source doesn't poison the pipeline | Sprint-2 | 3 | Ready | R-002 | —
IB-21 | Reliability & Resilience | LLM cost guard per cycle | platform owner | the Curator to halt if a single cycle exceeds a USD cap | a runaway prompt loop can't bill $1000 | Sprint-2 | 3 | Ready | R-003 | Curator-0004
IB-22 | Reliability & Resilience | Queue workers as docker services with restart=always | ops | Laravel queue:work and schedule:work to auto-restart | the Iniciar Scraping button never silently stops | Sprint-2 | 2 | Ready | R-008 | Platform-0008
IB-23 | Reliability & Resilience | DO Managed Postgres restore drill (monthly) | platform owner | to validate every month that I can actually restore | R-004 stops being a theoretical risk | Sprint-3 | 3 | Ready | R-004 | —
IB-24 | Reliability & Resilience | Two-Droplet active-active for the Reader (HA path) | platform owner | the Reader to survive a single Droplet failure | SLA can credibly claim 99.9% | Sprint-4 | 5 | Ready | R-005 | —
IB-25 | Data Architecture | Reset pgvector dimension to 1024 (bge-m3) | Curator | articles.embedding to be vector(1024) matching bge-m3 | pipeline doesn't crash on insert | Sprint-2 | 2 | Ready | R-011 | —
IB-26 | Data Architecture | Schema migrations runner | team | a real migrations system with versions and tracking | structural DB changes are reproducible | Sprint-3 | 3 | Ready | R-011-followup | Platform-0010
IB-27 | Data Architecture | IVFFlat lists tuning playbook | Curator | rules for when to rebuild pgvector index with different lists | cluster latency stays under 100ms as data grows | Sprint-4 | 2 | Ready | R-006 | —
IB-28 | Data Architecture | Split inkbytes package into legacy + contracts | platform team | the legacy v1 models separated from the v2 contracts | Curator can move forward without dragging Messor | Sprint-4 | 3 | Ready | R-010 | —
IB-29 | Data Architecture | Article retention + archival policy | platform owner | a clear policy for how long we keep articles/embeddings | DB doesn't grow unbounded | Sprint-3 | 3 | Ready | R-006 | —
IB-30 | LLM Quality & Provenance | Two-pass fact-check on SYNTHESIZE output | platform owner | every published one-pager to pass an LLM verification step | R-001 is materially mitigated | Sprint-3 | 5 | Ready | R-001 | —
IB-31 | LLM Quality & Provenance | Per-claim provenance markers in synthesis_md | reader | to see which source supports each claim | I can verify the synthesis matches the sources | Sprint-3 | 3 | Ready | R-001 | Reader-0002
IB-32 | LLM Quality & Provenance | Cluster quality evaluation dataset (100 hand-labeled events) | platform team | a gold dataset to measure precision/recall | tune thresholds with evidence not vibes | Sprint-3 | 3 | Ready | R-007 | —
IB-33 | LLM Quality & Provenance | Prompt replay test harness | team | to replay any prompt edit against frozen fixtures before merging | prompt regressions don't ship unnoticed | Sprint-3 | 3 | Ready | R-001 | —
IB-34 | LLM Quality & Provenance | Lock brand voice for SYNTHESIZE prompt | product owner | the SYNTHESIZE prompt to enforce one brand voice | every one-pager reads consistent and on-brand | Sprint-3 | 2 | Ready | R-013 | Reader-0001
IB-35 | Deploy & CI/CD | .do/app.yaml for DO App Platform autodeploy | platform owner | every push to master to autodeploy | I don't ssh into servers to ship code | Sprint-2 | 5 | Ready | — | Was-INK-8
IB-36 | Deploy & CI/CD | CI pipeline (lint + test + image build) | team | every PR to run ruff + pytest + docker build | master never breaks silently | Sprint-2 | 3 | Ready | — | Was-INK-9
IB-37 | Deploy & CI/CD | One-command rollback runbook | ops | a single documented command to roll back any service | I can recover from a bad deploy in <2 min | Sprint-2 | 1 | Ready | R-005 | —
IB-38 | Deploy & CI/CD | Staging environment with mirror config | team | a staging deploy mirroring prod with separate buckets/vhosts | soak tests don't contaminate prod | Sprint-3 | 2 | Ready | — | —
IB-39 | Deploy & CI/CD | 7-day staging soak as ship-gate | platform owner | every release candidate to run 7 days on staging unattended | v0 ship is evidence-based | Sprint-3 | 2 | Ready | — | Was-INK-10
IB-40 | Observability | Better Stack log aggregation (free tier) | ops | all service logs in one searchable UI | debugging doesn't require ssh | Sprint-3 | 2 | Ready | — | —
IB-41 | Observability | OpenTelemetry tracing across services | team | distributed traces showing the full path harvest→publish | I can pinpoint latency | Sprint-3 | 3 | Ready | — | —
IB-42 | Observability | Prometheus metrics on every FastAPI service | team | RED metrics + LLM cost counters | dashboards are populated and alerts are objective | Sprint-3 | 3 | Ready | — | —
IB-43 | Observability | Cost & quality dashboard in Backoffice | operator | a single Backoffice page showing today's USD spend + errors + freshness | I see system health without leaving admin | Sprint-4 | 3 | Ready | R-003 | —
IB-44 | Observability | Sentry error tracking (free tier) | team | unhandled exceptions to land in Sentry with stack + context | errors get triaged not buried in stdout | Sprint-3 | 2 | Ready | — | —
IB-45 | Pipeline Contracts | Lock inkbytes.article.v1 schema in packages/contracts/ | service | to depend on a versioned validated event schema | breaking changes are explicit | Sprint-2 | 3 | Ready | — | Was-INK-7
IB-46 | Pipeline Contracts | Lock inkbytes.session.v1 schema | Backoffice | scrape.session.completed to follow a stable schema | the run-history page doesn't break | Sprint-3 | 2 | Ready | — | Platform-0006
IB-47 | Pipeline Contracts | Lock PageV1 contract for Reader consumption | Reader | the page JSON returned by Curator to follow a stable contract | Next.js render is buildable independent of Curator | Sprint-3 | 2 | Ready | — | —
IB-48 | Pipeline Contracts | Schema evolution protocol document | team | a documented protocol for changing contract schemas safely | every change follows the same pattern | Sprint-3 | 2 | Ready | — | Platform-0011
IB-49 | Reader & Monetization | Magic-link email auth (Resend + Lucia) | reader | to log in with just my email (no password) | signup friction is near-zero | Sprint-4 | 5 | Ready | — | —
IB-50 | Reader & Monetization | Stripe Checkout + webhook → users.is_paid | reader | to subscribe with a credit card via Stripe Checkout | I can pay without leaving the site | Sprint-4 | 5 | Ready | — | —
IB-51 | Reader & Monetization | Free preview vs paid full read | non-paying visitor | to see headlines + first 100 words of each event | I can sample before paying | Sprint-4 | 2 | Ready | — | —
IB-52 | Reader & Monetization | Public API rate limiting per IP and per user | platform | rate limits on the Reader-facing API | scrapers can't lift our content | Sprint-4 | 2 | Ready | — | —
IB-53 | Reader & Monetization | Privacy policy + DSAR endpoint (DR Ley 172-13) | platform owner | a public privacy policy and admin DSAR endpoint | I'm aligned with DR data law before paying users | Sprint-4 | 3 | Ready | — | —

## Prioritization
ID | Story | Value (1-5) | Effort (1-5) | Risk/Uncert (1-5) | Score (V / (E+R)) | Recommendation
IB-12 | Rotate all legacy production-looking tokens | 5 | 1 | 1 | 2.5 | Quick win
IB-13 | Scrub leaked tokens from git history | 5 | 2 | 2 | 1.25 | Evaluate
IB-14 | Install pre-commit secret scanner (gitleaks) | 5 | 1 | 1 | 2.5 | Quick win
IB-15 | Enable GitHub secret scanning + push protection | 4 | 1 | 1 | 2 | Quick win
IB-16 | Move RabbitMQ from user/pass to TLS-cert auth | 4 | 3 | 3 | 0.67 | Strategic
IB-17 | External penetration test before second user cohort | 4 | 2 | 2 | 1 | Evaluate
IB-18 | Production Dockerfile + health endpoints for both services | 5 | 2 | 1 | 1.67 | Quick win
IB-19 | Tenacity retry wrapper around outbound HTTP | 5 | 2 | 1 | 1.67 | Quick win
IB-20 | Per-outlet circuit breaker in Messor | 4 | 2 | 2 | 1 | Evaluate
IB-21 | LLM cost guard per cycle | 5 | 2 | 1 | 1.67 | Quick win
IB-22 | Queue workers as docker services with restart=always | 4 | 1 | 1 | 2 | Quick win
IB-23 | DO Managed Postgres restore drill (monthly) | 5 | 2 | 2 | 1.25 | Evaluate
IB-24 | Two-Droplet active-active for the Reader (HA path) | 4 | 4 | 3 | 0.57 | Strategic
IB-25 | Reset pgvector dimension to 1024 (bge-m3) | 5 | 1 | 1 | 2.5 | Quick win
IB-26 | Schema migrations runner | 4 | 2 | 2 | 1 | Evaluate
IB-27 | IVFFlat lists tuning playbook | 3 | 2 | 2 | 0.75 | Evaluate
IB-28 | Split inkbytes package into legacy + contracts | 3 | 3 | 2 | 0.6 | Evaluate
IB-29 | Article retention + archival policy | 3 | 2 | 2 | 0.75 | Evaluate
IB-30 | Two-pass fact-check on SYNTHESIZE output | 5 | 3 | 3 | 0.83 | Strategic
IB-31 | Per-claim provenance markers in synthesis_md | 4 | 2 | 2 | 1 | Evaluate
IB-32 | Cluster quality evaluation dataset (100 hand-labeled events) | 4 | 2 | 1 | 1.33 | Quick win
IB-33 | Prompt replay test harness | 4 | 2 | 2 | 1 | Evaluate
IB-34 | Lock brand voice for SYNTHESIZE prompt | 4 | 1 | 2 | 1.33 | Quick win
IB-35 | .do/app.yaml for DO App Platform autodeploy | 5 | 3 | 2 | 1 | Evaluate
IB-36 | CI pipeline (lint + test + image build) | 5 | 2 | 1 | 1.67 | Quick win
IB-37 | One-command rollback runbook | 4 | 1 | 1 | 2 | Quick win
IB-38 | Staging environment with mirror config | 4 | 2 | 1 | 1.33 | Quick win
IB-39 | 7-day staging soak as ship-gate | 4 | 1 | 2 | 1.33 | Quick win
IB-40 | Better Stack log aggregation (free tier) | 5 | 1 | 1 | 2.5 | Quick win
IB-41 | OpenTelemetry tracing across services | 4 | 3 | 2 | 0.8 | Evaluate
IB-42 | Prometheus metrics on every FastAPI service | 4 | 2 | 1 | 1.33 | Quick win
IB-43 | Cost & quality dashboard in Backoffice | 4 | 2 | 2 | 1 | Evaluate
IB-44 | Sentry error tracking (free tier) | 5 | 1 | 1 | 2.5 | Quick win
IB-45 | Lock inkbytes.article.v1 schema in packages/contracts/ | 4 | 2 | 1 | 1.33 | Quick win
IB-46 | Lock inkbytes.session.v1 schema | 4 | 1 | 1 | 2 | Quick win
IB-47 | Lock PageV1 contract for Reader consumption | 4 | 1 | 1 | 2 | Quick win
IB-48 | Schema evolution protocol document | 3 | 1 | 2 | 1 | Evaluate
IB-49 | Magic-link email auth (Resend + Lucia) | 5 | 3 | 2 | 1 | Evaluate
IB-50 | Stripe Checkout + webhook → users.is_paid | 5 | 3 | 2 | 1 | Evaluate
IB-51 | Free preview vs paid full read | 4 | 1 | 1 | 2 | Quick win
IB-52 | Public API rate limiting per IP and per user | 3 | 2 | 1 | 1 | Evaluate
IB-53 | Privacy policy + DSAR endpoint (DR Ley 172-13) | 4 | 2 | 2 | 1 | Evaluate

## Sprint Plan
Sprint | ID | Epic | Story | Points
Sprint-2 | IB-12 | Security & Compliance | Rotate all legacy production-looking tokens | 2
Sprint-2 | IB-13 | Security & Compliance | Scrub leaked tokens from git history | 3
Sprint-2 | IB-14 | Security & Compliance | Install pre-commit secret scanner (gitleaks) | 2
Sprint-2 | IB-15 | Security & Compliance | Enable GitHub secret scanning + push protection | 1
Sprint-2 | IB-18 | Reliability & Resilience | Production Dockerfile + health endpoints for both services | 3
Sprint-2 | IB-19 | Reliability & Resilience | Tenacity retry wrapper around outbound HTTP | 3
Sprint-2 | IB-20 | Reliability & Resilience | Per-outlet circuit breaker in Messor | 3
Sprint-2 | IB-21 | Reliability & Resilience | LLM cost guard per cycle | 3
Sprint-2 | IB-22 | Reliability & Resilience | Queue workers as docker services with restart=always | 2
Sprint-2 | IB-25 | Data Architecture | Reset pgvector dimension to 1024 (bge-m3) | 2
Sprint-2 | IB-35 | Deploy & CI/CD | .do/app.yaml for DO App Platform autodeploy | 5
Sprint-2 | IB-36 | Deploy & CI/CD | CI pipeline (lint + test + image build) | 3
Sprint-2 | IB-37 | Deploy & CI/CD | One-command rollback runbook | 1
Sprint-2 | IB-45 | Pipeline Contracts | Lock inkbytes.article.v1 schema in packages/contracts/ | 3
Sprint-2 TOTAL |  |  |  | 36
Sprint-3 | IB-16 | Security & Compliance | Move RabbitMQ from user/pass to TLS-cert auth | 5
Sprint-3 | IB-23 | Reliability & Resilience | DO Managed Postgres restore drill (monthly) | 3
Sprint-3 | IB-26 | Data Architecture | Schema migrations runner | 3
Sprint-3 | IB-29 | Data Architecture | Article retention + archival policy | 3
Sprint-3 | IB-30 | LLM Quality & Provenance | Two-pass fact-check on SYNTHESIZE output | 5
Sprint-3 | IB-31 | LLM Quality & Provenance | Per-claim provenance markers in synthesis_md | 3
Sprint-3 | IB-32 | LLM Quality & Provenance | Cluster quality evaluation dataset (100 hand-labeled events) | 3
Sprint-3 | IB-33 | LLM Quality & Provenance | Prompt replay test harness | 3
Sprint-3 | IB-34 | LLM Quality & Provenance | Lock brand voice for SYNTHESIZE prompt | 2
Sprint-3 | IB-38 | Deploy & CI/CD | Staging environment with mirror config | 2
Sprint-3 | IB-39 | Deploy & CI/CD | 7-day staging soak as ship-gate | 2
Sprint-3 | IB-40 | Observability | Better Stack log aggregation (free tier) | 2
Sprint-3 | IB-41 | Observability | OpenTelemetry tracing across services | 3
Sprint-3 | IB-42 | Observability | Prometheus metrics on every FastAPI service | 3
Sprint-3 | IB-44 | Observability | Sentry error tracking (free tier) | 2
Sprint-3 | IB-46 | Pipeline Contracts | Lock inkbytes.session.v1 schema | 2
Sprint-3 | IB-47 | Pipeline Contracts | Lock PageV1 contract for Reader consumption | 2
Sprint-3 | IB-48 | Pipeline Contracts | Schema evolution protocol document | 2
Sprint-3 TOTAL |  |  |  | 50
Sprint-4 | IB-17 | Security & Compliance | External penetration test before second user cohort | 3
Sprint-4 | IB-24 | Reliability & Resilience | Two-Droplet active-active for the Reader (HA path) | 5
Sprint-4 | IB-27 | Data Architecture | IVFFlat lists tuning playbook | 2
Sprint-4 | IB-28 | Data Architecture | Split inkbytes package into legacy + contracts | 3
Sprint-4 | IB-43 | Observability | Cost & quality dashboard in Backoffice | 3
Sprint-4 | IB-49 | Reader & Monetization | Magic-link email auth (Resend + Lucia) | 5
Sprint-4 | IB-50 | Reader & Monetization | Stripe Checkout + webhook → users.is_paid | 5
Sprint-4 | IB-51 | Reader & Monetization | Free preview vs paid full read | 2
Sprint-4 | IB-52 | Reader & Monetization | Public API rate limiting per IP and per user | 2
Sprint-4 | IB-53 | Reader & Monetization | Privacy policy + DSAR endpoint (DR Ley 172-13) | 3
Sprint-4 TOTAL |  |  |  | 33
Capacity check (30 pts/sprint with 2 engineers):
Sprint-2: 36 pts ✅
Sprint-3: 50 pts ⚠️
Sprint-4: 33 pts ✅

## Summary
Counts by Epic
Epic | Story count | Total points
Security & Compliance | 6 | 16
Reliability & Resilience | 7 | 22
Data Architecture | 5 | 13
LLM Quality & Provenance | 5 | 16
Deploy & CI/CD | 5 | 13
Observability | 5 | 13
Pipeline Contracts | 4 | 9
Reader & Monetization | 5 | 17
TOTAL | 42 | 119